## Worksheet
Sales Forecasting - Advanced Project Plan
Quarterly Forecast ¦ Q2 2024 ¦ Prepared on: June 5, 2024
Project Phase | Task Description | Owner | Start Date | End Date | Status | Budget (USD) | Sales Target (USD)
1. Market Analysis & Research
Phase 1 | Competitor Benchmarking & SWOT Analysis | Alice Johnson (Marketing) | 2024-04-01 | 2024-05-15 | Active | $8,500 | $35,000
Phase 2 | Customer Segmentation & Demand Forecasting Model Design | Carlos Mendez (Analytics) | 2024-05-16 | 2024-06-30 | Pending | $15,750 | $89,500
2. Sales Strategy Development
Phase 3 | Product Positioning & Pricing Strategy Alignment | Sophia Lee (Sales Ops) | 2024-06-15 | 2024-07-31 | Pending | $6,300 | $65,800
Phase 4 | Channel Strategy & Partner Onboarding Plan | James Wong (Business Development) | 2024-07-15 | 2024-08-31 | Pending | $18,900 | $97,300
3. Forecast Validation & Reporting
Phase 5 | Data Validation & Model Calibration | Lucas Brown (Data Science) | 2024-08-15 | 2024-09-30 | Pending | $12,650 | $74,100
Phase 6 | Final Forecast Report & Executive Presentation Prep | Alice Johnson (Marketing) | 2024-09-15 | 2024-10-31 | Pending | $7,800 | $45,900
Total Forecasted Sales: | [5 empty] | $75,900 | $417,600