## Worksheet
Phase | Task Description | Responsible Team Member | Start Date | End Date | Status | Budget (USD)
Planning | Define sales objectives and target markets | Marketing Team Lead | 2024-01-05 | 2024-01-15 | In Progress | $5,000
Data Collection | Gather historical sales data and market trends | Data Analysts | 2024-01-16 | 2024-01-31 | Not Started | $3,500
Forecast Modeling | Develop predictive models using statistical methods | Analytics Team | 2024-02-01 | 2024-02-15 | Not Started | $8,000
Review & Validation | Validate forecasts with stakeholders and adjust as needed | Product Manager, CFO | 2024-02-16 | 2024-02-28 | Not Started | $4,500
Reporting & Presentation | Create final forecast report and present to leadership | Sales Director, Project Manager | 2024-03-01 | 2024-03-10 | Not Started | $3,000