## Worksheet
Sales Forecasting - Project Plan
Project Phase | Task Description | Responsible Team | Start Date | End Date | Status | Budget (USD)
Market Research | Conduct competitor analysis and customer surveys | Marketing Team | 2024-06-01 | 2024-06-15 | In Progress | $8,500.00
Data Collection | Gather historical sales data and market trends | Analytics Team | 2024-06-16 | 2024-07-15 | Pending | $15,000.00
Forecast Modeling | Develop predictive models using statistical tools | Data Science Team | 2024-07-16 | 2024-08-15 | Pending | $35,000.00
Validation & Review | Validate forecast accuracy with stakeholders and adjust assumptions | Finance & Leadership | 2024-08-16 | 2024-08-31 | Pending | $12,500.00
Reporting & Presentation | Create final report and present forecast to executive team | Project Manager | 2024-09-01 | 2024-09-15 | Pending | $6,800.00
Total Project Cost: | [5 empty] | $77,800.00
Prepared on:May 27, 2024¦ Version:1.0 - Business Use