## Worksheet
Project Name | Phase | Start Date | End Date | Responsible Team | Status | Forecasted Revenue ($)
Client X - Website Redesign | Discovery & Planning | 2024-01-15 | 2024-01-31 | Product & Design | In Progress | 85,000.00
Client X - Website Redesign | Development | 2024-02-01 | 2024-03-15 | Engineering | Not Started | 150,000.00
Client X - Website Redesign | Testing & QA | 2024-03-16 | 2024-03-31 | QA Team | Not Started | 50,000.00
Client X - Website Redesign | Deployment & Training | 2024-04-01 | 2024-04-15 | Implementation | Not Started | 35,000.00
Client Y - Mobile App Launch | User Research & Design | 2024-01-10 | 2024-02-15 | UX & Design | In Progress | 75,000.00
Client Y - Mobile App Launch | Development Sprint 1-3 | 2024-02-16 | 2024-05-31 | Engineering (iOS & Android) | In Progress | 350,000.00
Client Y - Mobile App Launch | Testing & UAT | 2024-06-15 | 2024-07-15 | QA & Client Team | Not Started | 80,000.00
Client Y - Mobile App Launch | Go-Live & Support (1 Month) | 2024-07-16 | 2024-08-15 | Support Team | Not Started | 45,000.00
Client Z - CRM Integration Project | Requirements Gathering | 2024-01-20 | 2024-01-31 | Solutions Team | In Progress | 65,000.00
Client Z - CRM Integration Project | System Design & API Development | 2024-02-15 | 2024-03-31 | Engineering (Backend) | In Progress | 185,000.00
Client Z - CRM Integration Project | Data Migration & Testing | 2024-04-15 | 2024-05-31 | Data & QA Team | Not Started | 75,000.00
Client Z - CRM Integration Project | Training & Go-Live | 2024-06-15 | 2024-06-30 | Implementation & Client Team | Not Started | 55,000.00
Total Forecasted Revenue: | [5 empty] | $1,185,000.00