## Worksheet
Task ID | Task Name | Start Date | End Date | Responsible Person | Status | % Complete | Budget (USD)
T001 | Data Collection - Historical Sales | 2024-01-15 | 2024-01-31 | Jane Doe | In Progress | 75% | $3,500.00
T002 | Market Research Analysis | 2024-01-16 | 2024-01-31 | Mike Smith | In Progress | 65% | $4,800.00
T003 | Customer Segmentation Modeling | 2024-02-01 | 2024-02-15 | Sarah Johnson | Not Started | 0% | $6,750.00
T004 | Sales Trend Forecasting (Model 1) | 2024-02-16 | 2024-03-15 | David Lee | Not Started | 0% | $7,900.00
T005 | Sales Trend Forecasting (Model 2) | 2024-03-16 | 2024-04-15 | Emily Chen | Not Started | 0% | $8,150.00
T006 | Risk Assessment & Scenario Planning | 2024-04-16 | 2024-05-15 | Lisa Wong | Not Started | 0% | $5,300.00
T007 | Forecast Validation & Adjustment | 2024-05-16 | 2024-06-15 | Jane Doe | Not Started | 0% | $3,850.00
Total Budget (USD) | [6 empty] | $41,250.00