## Worksheet
Sales Forecasting - Project Plan (Extended)
Project Phase | Task Name | Owner | Start Date | End Date | Status | Budget (USD) | Sales Forecast (USD)
Phase 1: Market Research
Market Analysis | Competitor Benchmarking | Jane Doe | 2025-04-01 | 2025-04-15 | Completed | $8,500.00 | $37,689.32
Market Analysis | Customer Segmentation Study | Mike Smith | 2025-04-16 | 2025-04-30 | Completed | $12,300.75 | $48,961.29
Phase 2: Forecast Model Development
Model Design | Build Regression Algorithm | Sarah Johnson | 2025-05-01 | 2025-06-14 | In Progress | $34,879.99 | $187,634.55
Model Design | Data Validation & Testing | David Lee | 2025-06-15 | 2025-07-15 | Delayed | $18,493.33 | $94,287.66
Phase 3: Integration & Deployment
System Integration | API Connection Setup | Anna Brown | 2025-07-16 | 2025-08-31 | Delayed | $47,983.45 | $369,452.17
Phase 4: Training & Rollout
Training Program | Develop Sales Team Materials | Sophia Garcia | 2025-09-01 | 2025-10-31 | Completed | $19,456.88 | $78,643.29
Phase 5: Review & Optimization
Performance Monitoring | Forecast Accuracy Analysis | Liam Wilson | 2025-11-01 | 2025-12-31 | Delayed | $36,789.44 | $654,889.77
Total Project Cost & Forecast Summary |  |  |  | Total |  | $185,403.84 | $1,526,970.39