## Worksheet
Sales Forecasting - Freelancer Project Plan
Task ID | Task Description | Assigned To | Start Date | End Date | Status | % Complete
001 | Market Research & Competitor Analysis | Jane Doe (Research Lead) | 2025-04-01 | 2025-04-15 | In Progress | 75%
002 | Data Collection from CRM & Sales Records | Mark Lee (Data Analyst) | 2025-04-16 | 2025-04-30 | Not Started | 0%
003 | Sales Trend Analysis (Historical Data) | Anna Smith (Forecasting Specialist) | 2025-05-01 | 2025-05-14 | Not Started | 0%
004 | Campaign Impact Assessment (Q1) | Liam Brown (Marketing Analyst) | 2025-05-15 | 2025-05-31 | Not Started | 0%
005 | Forecast Model Development (Regression) | Sophia Garcia (Data Scientist) | 2025-06-01 | 2025-06-14 | Not Started | 0%
006 | Model Validation & Accuracy Testing | Sophia Garcia (Data Scientist) | 2025-06-15 | 2025-06-30 | Not Started | 0%
007 | Presentation Draft & Report Writing | Jane Doe (Project Lead) | 2025-07-01 | 2025-07-14 | Not Started | 0%
008 | Final Review & Client Presentation | Jane Doe (Project Lead) | 2025-07-15 | 2025-07-31 | Not Started | 0%