## Worksheet
Sales Forecasting - Project Plan
Phase | Task Description | Start Date | End Date | Status | Responsible Team Member
Planning & Research | Gather historical sales data and market trends. | 2024-01-05 | 2024-01-15 | In Progress | John Doe
Data Analysis | Analyze past performance and identify forecasting patterns. | 2024-01-16 | 2024-01-30 | Not Started | Jane Smith
Model Development | Create forecasting model using regression and trend analysis. | 2024-01-31 | 2024-02-15 | Not Started | Alex Johnson
Validation & Testing | Validate model accuracy with historical data and adjust parameters. | 2024-02-16 | 2024-02-28 | Not Started | Lisa Chen
Forecast Output | Generate 12-month sales forecast with confidence intervals. | 2024-03-01 | 2024-03-15 | Not Started | Daniel Brown
Review & Presentation | Presentation of forecast to stakeholders and final approval. | 2024-03-16 | 2024-03-31 | Not Started | Sarah Wilson