## Worksheet
Sales Forecasting - Project Plan (Manager View)
Phase | Task | Owner | Start Date | End Date | Status | Budget (USD) | Forecasted Revenue (USD)
Phase 1 Market Research | Conduct market analysis | Jane Cooper | 2024-01-15 | 2024-02-15 | In Progress | $8,500 | $75,000
| Identify key customer segments | Michael Reed | 2024-01-25 | 2024-03-15 | In Progress | $6,750 | $98,000
| Review competitive landscape | Lisa Patel | 2024-02-15 | 2024-03-31 | In Progress | $7,800 | $89,500
Phase 2 Sales Strategy | Define target pricing tiers | Robert Turner | 2024-03-15 | 2024-04-15 | In Progress | $9,600 | $187,000
| Develop sales playbook and scripts | Sarah Hughes | 2024-04-15 | 2024-05-31 | In Progress | $11,350 | $236,800
| Design incentive structures for sales team | David Kim | 2024-05-15 | 2024-06-30 | In Progress | $8,950 | $178,200
Phase 3 Forecasting Model | Build predictive analytics model | Amy Wu | 2024-06-15 | 2024-08-15 | In Progress | $35,400 | $986,700
| Validate model accuracy with historical data | James Lee | 2024-08-15 | 2024-10-31 | Delayed (Pending) | $19,800 | $593,400
Phase 4 Implementation | Deploy forecasting tool across teams | Nina Gonzales | 2024-11-01 | 2025-01-31 | In Progress | $48,950 | $678,900
| Train sales and leadership teams | Carlos Mendez | 2025-01-15 | 2025-03-31 | Delayed (Pending) | $18,750 | $496,200
Total Project Cost & Forecasted Revenue | [5 empty] | $217,850 | $4,132,700