## Worksheet
Sales Forecasting - Project Plan (Multi-Page)
Project:Sales Forecasting InitiativeVersion:2.0Date:April 5, 2024
Sales Forecasting - Project Plan (Page 1: Overview)
Phase | Objective | Start Date | End Date | Status
Phase 1: Data Collection | Gather historical sales data, market trends, and customer insights. | 2024-04-05 | 2024-05-15 | In Progress
Phase 2: Data Processing & Cleaning | Standardize, validate, and clean data sets for accuracy. | 2024-05-16 | 2024-06-15 | Pending
Phase 3: Model Development | Build predictive models using statistical and ML techniques. | 2024-06-16 | 2024-07-31 | Pending
Phase 4: Validation & Testing | Validate model accuracy and test predictions against real outcomes. | 2024-08-01 | 2024-08-31 | Pending
Phase 5: Deployment & Integration | Integrate forecasting system into CRM and reporting platforms. | 2024-09-01 | 2024-10-15 | Pending
Phase 6: Training & Support | Train sales and leadership teams on using the forecasting tool. | 2024-10-16 | 2024-10-31 | Pending
Sales Forecasting - Project Plan (Page 2: Detailed Task Breakdown)
Task ID | Task Description | Owner | Due Date | Status | Priority
T001 | Collect historical sales data (2021–2023) | Alice Chen (Data Analyst) | 2024-05-15 | In Progress | High
T002 | Clean and format raw sales datasets (remove duplicates, missing values) | James Lee (Data Engineer) | 2024-06-15 | Pending | High
T003 | Extract market trend data from third-party sources (e.g., Statista, Gartner) | Sarah Kim (Market Research) | 2024-06-15 | Pending | Medium
T004 | Develop linear regression model for baseline forecasting | Dr. Robert Taylor (Data Scientist) | 2024-07-31 | Pending | High
T005 | Implement time-series forecasting using ARIMA models | Lisa Wang (Data Scientist) | 2024-07-31 | Pending | High
T006 | Train and evaluate machine learning models (Random Forest, XGBoost) | Elena Rodriguez (ML Engineer) | 2024-08-15 | Pending | High
T007 | Compare model accuracy using RMSE and MAPE metrics | Marcus Johnson (Data Analyst) | 2024-08-31 | Pending | High
T008 | Integrate top-performing model into internal dashboard (Power BI) | David Park (BI Developer) | 2024-10-15 | Pending | High
T009 | Create training materials and user guides for forecasting tool | Sophia Bennett (Training Specialist) | 2024-10-31 | Pending | Medium
Sales Forecasting - Project Plan (Page 3: Key Metrics & KPIs)
KPI | Target | Current Value | Status
Average Forecast Accuracy (MAPE) | < 10% | 14.2% | On Track
Data Completeness Rate | ≥ 98% | 96.5% | Pending Improvement
Model Training Time (per iteration) | < 10 minutes | 12.4 minutes | Pending Optimization
User Adoption Rate (after training) | ≥ 80% | N/A | Pending
Sales Forecasting - Project Plan (Page 4: Risks & Dependencies)
Risk / Dependency | Impact | Probability | Mitigation Strategy
Data from legacy CRM system is incomplete or inconsistent. | High | Medium | Implement data validation scripts and manual verification process.
Delays in third-party market data licensing. | Medium | Low | Negotiate early access; use proxy indicators if needed.
Team bandwidth constraints during model development phase. | High | Medium | Reallocate resources; hire temporary contractor if required.
Sales Forecasting - Project Plan (Page 5: Summary & Next Steps)
Section | Summary
Status Overview | The project is in Phase 1: Data Collection, with overall timeline on track. Key risks identified and mitigation plans established.
Next Steps | Complete data collection by May 15; initiate data cleaning process; assign model developers.
Upcoming Milestones | • Data Cleaned: June 15 • Model Development Completed: July 31 • Full System Testing: August 31