## Worksheet
Sales Forecasting - Project PlanOffice Use Template ¦ Prepared for Strategic Planning & Business Development
Project Phase | Task Description | Responsible Team/Person | Start Date | End Date | Status | Budget Allocation (USD)
Planning & Research | Collect historical sales data (Q1–Q4 2023) | Sales Analytics Team | 2024-01-05 | 2024-01-15 | In Progress | $8,500
| Analyze market trends and competitor pricing | Market Research Group | 2024-01-16 | 2024-01-31 | Pending Review | $6,750
| Define forecast assumptions and methodology | Forecasting Lead, Finance Dept. | 2024-02-01 | 2024-02-10 | To Do | $3,500
Model Development | Build statistical forecasting model (regression, time series) | Data Science Team | 2024-02-11 | 2024-03-15 | To Do | $18,900
| Validate model accuracy using historical data | Quality Assurance & Analytics | 2024-03-16 | 2024-03-31 | To Do | $5,450
| Integrate model into CRM and reporting dashboards | IT & Integration Team | 2024-04-01 | 2024-04-15 | To Do | $15,300
Forecasting & Reporting | Generate Q2–Q4 2024 sales forecast (by region & product) | Sales Forecasting Team | 2024-04-16 | 2024-05-15 | To Do | $13,800
| Prepare executive summary and visual reports (charts & graphs) | Reporting & Strategy Office | 2024-05-16 | 2024-05-31 | To Do | $7,600
| Presentation to Leadership & Feedback Integration | CPO & Finance Directors | 2024-06-01 | 2024-06-15 | To Do | $3,950
Total Estimated Budget: | [5 empty] | $94,750
This document is intended for internal use only. All data and projections are subject to change based on market conditions. Version: 1.0 ¦ Created: January 2024