## Worksheet
Sales Forecasting - Project Plan (One Page)
Project Phase | Key Activities | Responsible Team | Start Date | End Date | Status | Budget (USD)
Market Research & Analysis | Collect market data, analyze trends, identify customer segments. | Marketing & Analytics | 2024-04-01 | 2024-04-15 | In Progress | $8,500
Data Collection & Validation | Gather historical sales data, validate accuracy with finance. | Data Management Team | 2024-04-16 | 2024-04-30 | Not Started | $5,000
Sales Forecast Modeling | Develop forecasting models using historical and market data. | Data Science & Finance | 2024-05-01 | 2024-05-15 | Not Started | $12,000
Scenario Planning & Sensitivity Analysis | Create best-case, worst-case, and base-case scenarios. | Finance & Strategy | 2024-05-16 | 2024-05-31 | Not Started | $7,500
Review & Approval Session | Presentation to leadership for feedback and approval. | Project Lead & Executives | 2024-06-01 | 2024-06-10 | Not Started | $3,500
Total Project Budget: | [5 empty] | $36,500