## Worksheet
Sales Forecasting - Project Plan
Project Phase | Task Description | Owner | Start Date | End Date | Status | Budget (USD)
Planning & Research | Analyze market trends and historical sales data. | Jane Doe | 2024-01-05 | 2024-01-15 | In Progress | 3,500.00
Data Collection | Gather quarterly sales records from regional teams. | John Smith | 2024-01-16 | 2024-01-31 | Pending | 2,800.00
Forecast Modeling | Develop predictive models using statistical tools. | Lisa Chen | 2024-02-01 | 2024-02-15 | Not Started | 5,600.00
Validation & Testing | Validate model accuracy with historical data. | Robert Kim