## Worksheet
Sales Forecasting - Project Plan
Professional Template for Sales Planning & Forecasting
Project Phase | Task Description | Responsible Team | Start Date | End Date | Status | Sales Target (USD)
Planning & Research | Market Analysis and Competitor Benchmarking | Market Research Team | 2024-01-15 | 2024-01-31 | Pending | $5,000,000
Forecast Development | Create Monthly Sales Forecast Model | Data Analytics Team | 2024-02-15 | 2024-03-15 | In Progress | $7,890,500
Strategy Implementation | Liaise with Sales & Marketing for Campaign Rollout | Sales & Marketing Team | 2024-03-16 | 2024-05-31 | In Progress | $9,500,750
Performance Review | Monthly Forecast vs Actual Analysis & Adjustment | Finance & Operations Team | 2024-04-15 | 2024-12-31 | Pending | $6,750,000
Reporting & Optimization | Generate Quarterly Forecast Report for Leadership Review | Executive Reporting Team | 2024-11-15 | 2024-12-31 | Pending | $8,900,350