## Worksheet
Sales Forecasting - Project Plan Report VersionMonthly Sales Projections & Key Milestones
Project Phase | Task Description | Responsible Team | Start Date | End Date | Status | Sales Forecast (USD) | Milestone Achieved? | Risk Level
Planning & Research | Market Analysis and Competitor Review | Marketing & Sales Team | 2024-01-05 | 2024-01-15 | In Progress | $85,673.49 | No | Medium
Forecast Modeling | Build Predictive Sales Models using Historical Data | Data Science Team | 2024-01-16 | 2024-02-15 | In Progress | $347,895.36 No High
Promotion Strategy | Develop Launch Campaigns and Channels | Marketing Team | 2024-02-16 | 2024-03-15 | Pending | $98,347.85 No Low
Implementation Phase 1 | Deploy Forecasting Tools in Sales Portal | IT & Dev Team | 2024-03-16 | 2024-04-15 | In Progress $765,987.12 No Medium
Testing & Validation | User Testing and Forecast Accuracy Review | QA Team & Sales Ops | 2024-04-16 | 2024-05-15 | Pending $639,178.43 No Low
Full Rollout & Reporting | Company-wide Implementation and Monthly Forecast Reports | Sales & Analytics Team | 2024-05-16 | 2024-06-30 | Pending $1,875,938.77 No Low
Total Projected Sales: | [5 empty] | $4,513,805.03 | — | —