## Worksheet
Sales Forecasting - Project Plan (Small Business)
Phase | Task | Owner | Start Date | End Date | Status | Budget ($)
Planning | Define Sales Objectives | Jane Doe | 2024-04-01 | 2024-04-05 | In Progress | 1,500
Planning | Market Research & Competitor Analysis | John Smith | 2024-04-06 | 2024-04-15 | To Do | 3,200
Data Collection | Gather Historical Sales Data | Sara Lee | 2024-04-16 | 2024-04-25 | To Do | 1,800
Data Analysis | Analyze Trends & Seasonality | Mike Brown | 2024-04-26 | 2024-05-05 | To Do | 2,500
Forecasting | Create Sales Forecast Models (Q2) | Jane Doe | 2024-05-06 | 2024-05-15 | To Do | 3,750
Review & Approval | Presentation to Management Team | John Smith | 2024-05-16 | 2024-05-18 | To Do | 800
Total Estimated Budget: | [5 empty] | $13,550