## Worksheet
Sales Forecasting - Project Plan (Team Use)
Phase | Task | Owner | Start Date | End Date | Status | % Complete
1. Planning & Preparation
1.1 | Define sales objectives and KPIs | John Smith | 2024-04-01 | 2024-04-05 | In Progress | 75%
1.2 | Gather historical sales data | Sarah Johnson | 2024-04-06 | 2024-04-10 | Not Started | 0%
2. Data Analysis & Modeling
2.1 | Conduct market trend analysis | Alex Rodriguez | 2024-04-11 | 2024-04-18 | In Progress | 50%
2.2 | Develop forecasting model (Regression) | Lisa Wong | 2024-04-19 | 2024-04-30 | In Progress | 65%
3. Validation & Review
3.1 | Validate model accuracy with historical data | Daniel Kim | 2024-05-01 | 2024-05-07 | Not Started | 0%
3.2 | Pilot test with Q2 forecast scenario | Sarah Johnson | 2024-05-08 | 2024-05-15 | Not Started | 0%
4. Reporting & Deployment
4.1 | Create executive summary and visual dashboards | John Smith | 2024-05-16 | 2024-05-23 | Not Started | 0%
4.2 | Presentation to leadership team (Q2 Forecast) | Lisa Wong | 2024-05-30 |  |  | Not Started
Final Project Status Summary
Overall Progress: |  |  |  | 52%