## Worksheet
Sales Forecasting - Project TimelineBusiness Use Template
Phase | Task Description | Start Date | End Date | Status | Owner/Team | Budget (USD) | KPI Target
1. Planning | Define forecasting objectives and scope | 2023-10-01 | 2023-10-15 | In Progress | Sales Ops Team | $5,000 | Clear KPI definition set
2. Data Collection | Gather historical sales data and market indicators | 2023-10-16 | 2023-11-05 | Not Started | Data Analytics Team | $8,500 | Data accuracy > 95%
3. Model Development | Build and test forecasting models (regression, time series) | 2023-11-06 | 2023-11-30 | In Progress | Data Science Team | $15,000 | MSE below 5%
4. Validation & Review | Validate model with historical data and stakeholder feedback | 2023-12-01 | 2023-12-15 | Pending Review | Product & Finance Leads | $4,000 | Model acceptance rate: 95%
5. Deployment | Implement forecasting tool into CRM and reporting systems | 2023-12-16 | 2024-01-15 | Not Started | Tech Integration Team | $18,000 | All key departments trained by deadline
6. Monitoring & Optimization | Monitor forecast accuracy and refine model monthly | 2024-01-16 | Ongoing | Not Started | Sales Analytics Team | $3,500/month | Average forecast error: ≤ 8%
Note:This table is designed for business use and can be imported into Excel. Adjust dates, budgets, and team assignments as needed.