## Worksheet
Sales Forecasting - Project Timeline (Detailed)
Phase | Task Description | Start Date | End Date | Status | Owner | Budget (USD) | Sales Forecast (USD)(Monthly)
Planning | Define Sales Goals & KPIs | 2024-01-01 | 2024-01-15 | In Progress | Jane Smith | $5,000 | $75,000(Jan)$83,256(Feb)$91,843(Mar)
| Market Research & Analysis | 2024-01-16 | 2024-01-31 | In Progress | Mike Johnson | $8,500 | $75,000 $83,256 $91,843(Jan- Mar)$125k (Q1 Est.)
| Resource Allocation & Team Setup | 2024-02-01 | 2024-02-15 | Pending | Sarah Lee | $6,300 | $75,000 $83,256 $91,843 $125k (Q1 Est.)$275k (Q2 Est.)$476k (H1 Est.)
Execution | Lead Generation Campaigns Launch | 2024-03-01 | 2024-06-30 | Pending | David Kim | $45,895 | $118k $137k $156k $172k (Q2)$360k (H2 Est.) $690k (YTD Est.)
| Client Onboarding & Training | 2024-04-15 | 2024-12-31 | Pending | Alice Brown | $37,689 | $168k $192k $205k $240k (Q3) $450k (H3 Est.) $798k (YTD Est.)
| Quarterly Sales Review & Adjustment | 2024-06-15 | 2024-06-30 | Pending | Jane Smith | $8,975 | $178k $235k $265k $294k (Q3) $490k (H3 Est.) $840k (YTD Est.)
Monitoring & Reporting | Monthly Performance Dashboards | 2024-01-05 | 2024-12-31 | In Progress | Sarah Lee | $3,567 | $98k $136k $158k $207k (Q4) $520k (H4 Est.) $980k (YTD Est.)
| Forecast Accuracy Review & Updates | 2024-10-15 | 2024-12-31 | Pending | Mike Johnson | $6,980 | $376k $458k $510k $542k (YTD)$1.1M (Annual Forecast)$1.2M (Adjusted Forecast)
Total Estimated Projected Revenue | [5 empty] | $253,406 | $1,200,000+($1.1M to $1.3M)