## Worksheet
Sales Forecasting - Project Timeline (Extended Version)
Phase | Start Date | End Date | Description | Forecasted Revenue (USD) | Status
Phase 1: Planning & Research | Jan 01, 2024 | Jan 31, 2024 | Market analysis, target audience definition, competitive research. |  | In Progress
| Conduct comprehensive market analysis and customer segmentation. |  |  |  |  | Completed
Phase 2: Strategy Development | Feb 01, 2024 | Mar 15, 2024 | Define sales strategies, pricing models, and promotional plans. |  | In Progress
| Develop sales strategy including channel selection and KPIs. |  |  |  |  | Completed
| Establish pricing tiers based on market research and margin targets. |  |  |  |  | In Progress
Phase 3: Forecasting & Modeling | Mar 16, 2024 | Apr 30, 2024 | Create predictive models using historical and market data. |  | In Progress
| Compile sales history, seasonality trends, and pipeline data. |  |  |  |  | Completed
| Build statistical forecasting models (regression, time series). |  |  |  |  | Completed
| Run best-case, worst-case, and base-case scenarios for revenue projection. |  |  |  |  | In Progress
Phase 4: Approval & Rollout | May 01, 2024 | Jun 15, 2024 | Gather stakeholder feedback and implement forecast in sales tools. |  | Not Started
| Present forecasts to leadership for review and validation. |  |  |  |  | Not Started
Phase 5: Monitoring & Adjustment | Jun 16, 2024 | Dec 31, 2024 | Track actual sales vs forecast and refine models monthly. |  | Not Started
| Conduct monthly performance reviews and update forecasts based on new data. |  |  |  |  | Not Started
Total Forecasted Revenue (2024) | $1,875,000 |  |  |  | Projected