## Worksheet
Sales Forecasting - Project Timeline (Freelancer Style)
Phase | Task Description | Start Date | End Date | Status | Budget (USD)
Phase 1: Initial Research | Market Analysis & Competitor Review | 2024-04-05 | 2024-04-15 | In Progress | $850
| Data Collection from CRM & Past Sales Reports | 2024-04-06 | 2024-04-18 | In Progress | $1,150
| Identify Key Sales Trends & Customer Segments | 2024-04-16 | 2024-04-25 | Pending | $750
Phase 2: Forecast Modeling | Develop Sales Projection Model (Time Series) | 2024-04-18 | 2024-05-10 | Pending | $3,500
| Apply Historical Patterns & Seasonal Adjustments | 2024-05-11 | 2024-05-28 | Pending | $3,750
| Validate Model with Historical Data (Accuracy Check) | 2024-05-29 | 2024-06-15 | Pending | $1,875
Phase 3: Reporting & Delivery | Create Visual Forecast Reports (Excel & Dashboard) | 2024-06-16 | 2024-07-05 | Pending | $1,950
| Prepare Presentation & Executive Summary | 2024-07-06 | 2024-07-15 | Pending | $1,450
| Client Review & Final Delivery (PDF + Excel) | 2024-07-16 | 2024-07-31 | Pending | $950
Total Project Budget: |  |  |  |  | $17,275
This forecast timeline is designed for freelancers and independent consultants to track key milestones, deliverables, and budgets in sales forecasting projects.