## Worksheet
Sales Forecasting - Project Timeline (Home Use)
Project Phase | Start Date | End Date | Key Milestones | Responsible Team | Status
Market Research & Analysis | 2023-10-01 | 2023-10-15 | Competitor analysis, customer survey completion, demand estimation | Marketing & Analytics | In Progress
Sales Strategy Development | 2023-10-16 | 2023-10-31 | Target market definition, pricing model, promotion plan | Sales & Strategy Team | Pending
Product Launch Planning | 2023-11-01 | 2023-11-15 | Launch timeline, inventory planning, sales training sessions | Operations & Sales | Pending
Initial Sales Campaign (Q4) | 2023-11-16 | 2023-12-31 | Digital ads, email marketing, partner promotions | Marketing & Sales | Pending
Forecast Review & Adjustment (Mid-Q4) | 2023-12-15 | 2023-12-31 | Performance evaluation, forecast update, action planning | All Teams | Pending
Q1 Forecast Planning (Preparation) | 2023-12-01 | 2024-01-15 | Data consolidation, trend analysis, goal setting for Q1 2024 | Finance & Sales Analytics | Pending
Q1 Forecast Execution (Q1 2024) | 2024-01-01 | 2024-03-31 | Daily tracking, weekly reviews, customer outreach campaigns | Sales & Operations | Pending
Total Duration: | 2023-10-01 to 2024-03-31 (6 Months) |  | Estimated Revenue: $578,950