## Worksheet
Project Phase | Task Name | Owner | Start Date | End Date | Status | Budget (USD)
Planning Phase
Project Initiation | Define Sales Goals & KPIs | Jane Smith | 2024-01-05 | 2024-01-15 | In Progress | $5,000
Market Analysis | Competitor & Industry Research | Mike Johnson | 2024-01-16 | 2024-01-31 | Pending | $8,500
Forecasting Phase
Sales Modeling | Develop Sales Forecast Model (Q1) | Sarah Lee | 2024-02-01 | 2024-02-15 | Pending | $15,000
Sales Modeling | Refine Model with Historical Data | Sarah Lee | 2024-02-16 | 2024-03-15 | Pending | $18,000
Execution Phase
Forecast Deployment | Finalize Forecast for Q2 & Q3 | David Kim | 2024-03-16 | 2024-04-15 | Pending | $12,000
Forecast Review & Approval | Executive Review Meeting - Q2 Forecast | Linda Brown (CEO) | 2024-04-16 | 2024-04-30 | Pending | $7,500
Monitoring & Reporting
Reporting Cycle 1 | Track Q2 Actual vs Forecast | Amy Patel | 2024-05-01 | 2024-05-31 | Pending | $6,000
Total Estimated Cost: | [5 empty] | $82,000