## Worksheet
Project Phase | Start Date | End Date | Owner(s) | Status | Budget (USD)
Market Research & Analysis | 2024-01-15 | 2024-02-15 | Jane Doe, Mike Smith | In Progress | $15,000
Product Planning & Design | 2024-02-16 | 2024-03-31 | Tom Lee, Sarah Johnson | In Progress | $35,000
Prototype Development | 2024-04-01 | 2024-05-15 | Rick Chen, Lisa Tran | Not Started | $50,000
Testing & QA Validation | 2024-05-16 | 2024-06-30 | Alice Brown, David Kim | Not Started | $25,000
Go-to-Market Launch | 2024-07-01 | 2024-08-31 | Jane Doe, Tom Lee | Not Started | $85,000
Sales Forecasting & Reporting | 2024-09-01 | 2024-11-30 | Mike Smith, Sarah Johnson | Not Started | $35,000
Team Use - This template is for internal sales forecasting and project timeline tracking. All data is subject to revision based on performance metrics.