## Worksheet
Phase | Key Milestones | Target Date | Status | Responsible Team | Budget Allocation ($)
Market Research & Validation | Complete customer surveys, analyze competitors, define unique value proposition | 2024-01-31 | In Progress | Product & Marketing | 15,000
Business Model Development | Define revenue streams, pricing strategy, customer segments, and channels | 2024-02-28 | To Do | Strategy & Finance | 10,000
Prototype Development | Build MVP (Minimum Viable Product) with core features | 2024-04-15 | To Do | R&D & Engineering | 50,000
User Testing & Feedback Loop | Conduct usability tests with 25+ beta users, gather feedback for iteration | 2024-05-31 | To Do | Product & UX Team | 8,000
Funding Round Preparation | Finalize pitch deck, financial projections, investor outreach plan | 2024-06-30 | To Do | Leadership & Finance | 12,000
Landing Page & Pre-Sales Campaign | Launch website with conversion tracking, initiate early-bird offers | 2024-07-15 | To Do | Marketing & Sales | 18,000
Product Launch (V1.0) | Official release to public with full feature set and support infrastructure | 2024-08-31 | To Do | All Teams | 45,000
Post-Launch Review & Iteration Plan | Evaluate KPIs, collect user feedback, plan V1.1 roadmap | 2024-10-31 | To Do | Product & Strategy | 7,500