## Worksheet
STARTUP PLANNING - ADVANCED BUSINESS TEMPLATE
Phase | Activity | Owner | Due Date | Status | Budget (USD) | Actual (USD) | % Complete | Notes
PHASE 1: CONCEPT & VISION
Concept Development | Define core mission, vision, and value proposition | CEO | 2023-10-15 | Completed | $5,000 | $4,850 | 100% | Mission statement approved by board.
Market Research | Conduct competitive analysis and customer persona development | Marketing Lead | 2023-11-01 | In Progress | $8,500 | $6,200 | 73% | Survey data collected from 254 participants.
PHASE 2: BUSINESS MODEL & STRATEGY
Business Model Design | Develop revenue streams, cost structure, and key partnerships | CTO/Strategy | 2023-11-15 | Pending | $6,000 | $0.00 | 5% | Waiting on feedback from investors.
Go-to-Market Plan | Create detailed launch strategy and channel distribution plan | Marketing Director | 2023-12-05 | Pending | $7,800 | $1,250 | 16% | Initial draft in progress.
PHASE 3: PRODUCT & TECHNOLOGY
Product Roadmap | Define MVP features and timeline for development | Product Manager | 2023-10-30 | Completed | $4,500 | $4,275 | 100% | MVP approved by engineering team.
PHASE 4: TEAM & OPERATIONS
Key Hires | Recruit core team members (Engineering, Sales, Ops) | HR Director | 2024-01-15 | In Progress | $50,000 | $32,800 | 66% | Two roles filled; three in interview stage.
PHASE 5: FUNDING & FINANCIALS
Financial Projections | Build 3-year P&L, cash flow, and balance sheet model | CFO | 2023-11-20 | Completed | $6,500 | $6,450 | 100% | Presentation ready for investor review.
TOTAL BUDGET & EXPENSES |  |  |  |  | $97,300 | $61,825 | —