## Startup Planning Dashboard
Startup Planning Dashboard
8Active Projects | 12Team Members | $2.4MFunding Raised | 90%Progress Rate
Task / Initiative | Owner | Due Date | Status | Priority
Business Model Validation | Alice Johnson | 2024-06-30 | In Progress | High
User Acquisition Strategy | Michael Chen | 2024-07-15 | In Progress | High
Seed Funding Pitch Deck | Sarah Williams | 2024-07-05 | Completed | High
Product Roadmap Planning | David Kim | 2024-06-30 | In Progress | High
Market Research & Competitor Analysis | Lisa Tran | 2024-06-25 | Completed | Medium
Legal & IP Registration | Robert Brown | 2024-07-10 | Delayed | High
Hiring: CTO Position | Elena Rodriguez | 2024-07-20 | In Progress | High
Initial MVP Development | Tom Lee | 2024-08-31 | In Progress | High
Custumer Feedback Loop Setup | Grace Patel | 2024-07-31 | In Progress | Medium
Partnership Outreach (Beta) | Nathan Wu | 2024-08-15 | Delayed | Medium
Beta Launch Preparation | Megan Foster | 2024-09-30 | In Progress | High
Next review scheduled on July 10, 2024