## Worksheet
Startup Planning - Extended Business Template
Phase | Key Activities |  |  |  | Timeline (Months) |  |  | Responsible Party | Status
| Activity Description | Deliverables | Resources Needed | Dependencies | Start | Middle | End
Phase 1: Ideation & Concept Validation
Market Research | Competitor analysis, customer surveys, SWOT report | Survey tools, analyst reports, focus groups | Preliminary concept development | 1 | 2.5 | 3-6 (Q1-Q2) | Product Team, Marketing Lead
Problem Validation | Customer pain point documentation, validation interviews | Interview templates, video recording tools | User feedback collection | 1.5
Value Proposition Design | Value proposition canvas, MVP concept draft | Whiteboards, design software (Figma/Miro) | MVP framework alignment
Total Time Allocated: |  | 4.5 months
Phase 2: Business Model & Funding Strategy
Business Model Canvas Development | Completed canvas document, revenue streams analysis | Canvas templates, financial modeling tools | Idea validation results | 4.5 (Q2)
Funding Strategy & Pitch Deck Creation | Pitch deck, investor outreach plan, funding milestone targets | Slide design tools (PowerPoint/Canva), investor database | Business model validation
Total Time Allocated: |  | 3 months
Phase 3: MVP Development & Testing
MVP Design & Prototyping | Interactive prototype, UX/UI mockups | Design software (Figma/Sketch), user testing tools | Value proposition approval | 6-9 (Q3)
Development Sprint 1-2 | Core product features implemented, testable build | Development team, Agile tools (Jira/Trello) | MVP design approval
Total Time Allocated: |  | 3 months
Phase 4: Launch & Growth Planning
Go-to-Market Strategy | Launch timeline, marketing campaigns, channel plan | Marketing automation tools (HubSpot/Mailchimp) | Funding secured, MVP tested | 9-12 (Q4)
Total Time Allocated: |  | 3 months
Overall Project Duration: | [7 empty] | 12 months | Active / In Progress
Legend:🟨 Highlighted= High priority items,🔵 Blue Header= Phase section,🟢 Status indicators
Startup Planning Template – Version Extended (v2.1) ¦ © 2024 Business Strategy Solutions