## Worksheet
Startup Planning Dashboard
Large Business Template ¦ Purpose: Business Planning & Strategy
STRATEGIC PLANNING FRAMEWORK
Phase | Key Initiative | Objective | Timeline (Months) | Budget Allocation ($K) | Status | Risk Level | Action Owner
Phase 1 | Market Research & Validation | Confirm target market demand and customer pain points | 0–3 | 150 | Active | Medium | Jane Doe, Research Lead
| Competitive Landscape Analysis | Identify key competitors and differentiators | 1–4 | 100 | On Hold | Medium | Mark Lee, Strategy Analyst
| Business Model Canvas Development | Create and refine the core business model structure | 2–6 | 75 | In Progress | Low | Lisa Chen, Product Manager
Phase 2 | Team Formation & Hiring Plan | Recruit core leadership team (Tech, Sales, Ops) | 3–8 | 400 | In Progress | Low | Ryan Kim, HR Director
| Product Development Roadmap (MVP) | Deliver a minimum viable product with core features | 4–12 | 600 | In Progress | Medium | David Patel, CTO
| Go-to-Market Strategy Design | Define marketing channels, pricing, and launch plan | 6–10 | 250 | On Hold | High | Sarah Thompson, Marketing Head
| Financial Projections & Funding Plan | Forecast 3-year P&L, cash flow, and investment needs | 8–14 | 125 | On Hold | Medium | Alex Morgan, CFO
Phase 3 | Product Beta Launch (Pilot) | Test MVP with select customers and collect feedback | 12–15 | 200 | Pending | High | Lisa Chen, Product Manager
| Full Market Launch (v1.0) | Official public release with marketing campaign | 16–20 | 800 | Pending | High | Sarah Thompson, Marketing Head
| Customer Acquisition & Retention Program | Implement onboarding, support, and retention strategies | 18–24 | 350 | Pending | Medium | James Wong, CXO
TOTAL PROJECT BUDGET: |  |  |  | $2,750K
Generated on: 2025-04-05 ¦ Version: 1.2 ¦ Template Type: Business - Large Business Style