## Startup Planning - Team Use
Startup Planning Template - Team Use
Project Phase | Key Objective | Responsible Team Member(s) | Deadline | Status | Notes/Comments
Market Research | Analyze target market trends and customer needs. | Marketing & Research Team | 2024-07-15 | In Progress | Competitor analysis ongoing.
Product Development | Create MVP prototype based on research findings. | Product & Engineering Team | 2024-08-30 | Pending | MVP design phase starts next week.
Business Model Design | Define revenue streams, pricing, and cost structure. | Finance & Strategy Team | 2024-07-25 | In Progress
Funding Strategy | Develop pitch deck and investor outreach plan. | CEO & Investor Relations | 2024-08-15 | Pending
Team Onboarding | Hire core team members and set up roles. | HR & Management | 2024-08-10 | Pending
Go-to-Market Plan | Create launch strategy and initial marketing campaign. | Marketing & Sales Team | 2024-09-15 | In Progress