## Worksheet
Startup Planning - Advanced Chore Chart
Track key tasks, responsibilities, and progress across your startup's foundational phases
Task / Responsibility | Owner | Priority | Due Date | Status | Progress Notes / Actions
Conduct Market Research & Validation | Marketing Lead | High | 2025-04-15 | Pending | Survey target customers, analyze competitors, finalize MVP concept.
Develop Business Model Canvas | CEO & Co-Founder | High | 2025-04-10 | Pending | Define value proposition, revenue streams, key partners.
Create MVP Prototype | Product Manager & Dev Team | High | 2025-05-30 | Ongoing | Wireframes completed. Development phase: UI/UX implementation.
Secure Seed Funding Pitch Deck | CEO & Finance Lead | Medium | 2025-06-15 | Pending | Refine investor messaging, incorporate feedback from mock presentations.
Build Core Team & Hire Key Roles | HR Director & CEO | High | 2025-06-30 | Pending | Finalize 3 critical hires: CTO, Head of Marketing, Lead Designer.
Establish Legal Structure & IP Protection | Legal Advisor & CEO | Medium | 2025-05-20 | Pending | Register LLC, draft NDAs, file patent application (if applicable).
Set Up Development & Collaboration Tools | CTO & IT Admin | Low | 2025-04-25 | Completed | Slack, Jira, GitHub, Notion workspace configured with role-based access.
Launch Pre-Launch Landing Page | Marketing Lead & Web Dev | High | 2025-04-30 | Completed | Collected 1,250 email sign-ups. A/B testing ongoing.
Last updated: April 5, 2025 ¦ Version v1.3 - Advanced Chore Chart Template