## Worksheet
Task | Responsible Team | Status | Deadline | Priority | Progress (%) | Metric/Output
Develop Business Model Canvas | Founders & Strategy Team | In Progress | 2024-04-15 | High | 75 | Draft completed, reviewed by 3 stakeholders.
Create MVP Scope & Features List | Product Team | Pending | 2024-04-18 | High | 0 | MVP feature document to be shared by April 17.
Secure Initial Seed Funding | CEO & Finance Lead | In Progress | 2024-05-01 | High | 50 | Awaiting term sheet from 2 VCs.
Build Core Development Team | Hiring Manager & CTO | In Progress | 2024-04-30 | High | 60 | 3/5 roles filled. Interview process ongoing.
Conduct Customer Discovery Interviews | Marketing & Product Teams | In Progress | 2024-04-19 | Medium | 85 | 25 interviews completed out of 30 targeted.
Set Up Legal Entity & IP Protection | Legal Counsel & Founders | Pending | 2024-04-25 | Medium | 0 | Limited to jurisdiction and documents.
Define KPIs & OKRs for Q2 | Operations & Leadership Team | In Progress | 2024-04-16 | Medium | 70 | KPI framework drafted for review.
Total Tasks: |  |  |  |  | 7 | —