## Worksheet
Annual Startup Planning Chore Chart
Month | Week | Chore Task | Status (Complete/In Progress/Pending) | Owner
January | 1-2 | Define vision and mission statement | Pending | Team Lead
Week 3-4: Market Research & Competitor Analysis
|  |  | Analyze target market demographics | Pending | Marketing Manager
|  |  | Compile competitor SWOT analysis | Pending | Business Analyst
February | Week 1-2: Legal & Registration Setup
|  |  | Register business entity (LLC, Corp, etc.) | Pending | Legal Advisor
|  |  | Obtain EIN and tax IDs | Pending | Finance Manager
|  |  | Secure business licenses & permits | Pending | Operations Lead
March | Week 1-2: Team Building & Hiring Plan
|  |  | Finalize job descriptions and roles | Pending | HR Manager
|  |  | Create recruitment strategy & timeline | Pending | <HR Manager
|  |  | Begin outreach to potential hires | Pending | Recruiter Team
April | Week 3-4: Financial Planning & Fundraising Prep
|  |  | Develop 12-month financial forecast (P&L, Cash Flow) | Pending | Finance Manager
|  |  | Create pitch deck for investors | Pending | CEO / Marketing Lead
|  |  | Identify and contact potential investors/VCs | Pending | CFO / Investor Relations
May | Week 1-2: Product Development Kickoff (Phase 1)
|  |  | Finalize MVP feature list | Pending | Product Manager
|  |  | Begin UI/UX design phase | Pending | Design Team
|  |  | Set up development environment & tools | Pending | <DevOps Lead
June | Week 3-4: Prototype Testing & Feedback Loop
|  |  | Develop functional prototype (MVP) | Pending | Engineering Team
|  |  | Conduct usability testing with 10 users | Pending | User Researcher
|  |  | Document feedback & plan revisions | Pending | Product Manager
July | Week 1-2: Funding Round Execution (Seed)
|  |  | Launch investor pitch presentations | Pending | CFO / CEO
|  |  | Negotiate term sheets & due diligence | Pending | Legal Advisor / CFO
August | Week 3-4: Team Expansion & Onboarding
|  |  | Onboard first 3 core team members (dev, marketing, product) | Pending | HR Manager / Team Leads
|  |  | Conduct orientation & culture training | Pending | HR Manager
September | Week 1-2: Pre-Launch Marketing Campaign
|  |  | Launch landing page & email list signup | Pending | Marketing Lead
October | Week 3-4: Beta Release & Feedback Collection
|  |  | Release public beta version to early users | Pending | Product Manager / Dev Team
November | Week 1-2: Finalize Product & Go-to-Market Strategy
|  |  | Implement top user feedback into final product | Pending | Product Manager / Dev Team
December | Week 3-4: Official Launch & Post-Launch Review
|  |  | Monitor performance: user acquisition, crashes, support tickets | Pending | Ops Team / Support