## Worksheet
Startup Planning - Detailed Chore Chart
Task ID | Task Description | Responsible Person(s) | Department/Team | Status | Prioritization Level | Scheduled Start Date | Scheduled End Date
Executive & Strategic Planning
SP-001 | Define company mission statement and vision for the next 5 years | CEO, CMO, Founder Team | Leadership | In Progress | High | 2024-04-15 | 2024-05-10
SP-002 | Establish 3 core strategic goals for Year 1 launch cycle | CXO Team, Board Members | Leadership, Strategy | To Do | High | 2024-05-15 | 2024-06-15
SP-003 | Conduct comprehensive competitor analysis (SWOT) for target market segment | Marketing, Strategy Analysts | Market Research, Marketing | In Progress | Medium | 2024-04-18 | 2024-05-30
SP-004 | Create 3-year financial forecast model (P&L, Cash Flow, Balance Sheet) | CTO, CFO | Finance & Operations | To Do | High | 2024-05-18 | 2024-07-15
Legal & Regulatory Compliance
LC-001 | Register business entity (LLC, Corporation) with state authorities | General Counsel, Legal Ops Manager | Legal Department | In Progress | High | 2024-04-10 | 2024-05-15
LC-002 | Pending patent filing for core technology and product IP | Legal Counsel, R&D Lead | IP & Innovation | To Do | High | 2024-06-01 | 2024-07-31
LC-003 | Ensure GDPR/CCPA compliance in data handling and user agreement templates | Data Protection Officer, Legal Team | Legal & IT Security | To Do | Medium | 2024-05-15 | 2024-06-30
Product Development & Innovation
PD-001 | Define minimum viable product (MVP) feature set and user story mapping | Product Manager, UX Lead, Engineering Lead | Product & Engineering | In Progress | High | 2024-04-12 | 2024-06-15
PD-002 | Develop high-fidelity interactive prototype for MVP testing phase | UI/UX Team, Frontend Devs | User Experience & Frontend | In Progress | High | 2024-05-10 | 2024-07-15
PD-003 | Create beta tester recruitment plan and feedback collection process | Product Manager, Marketing Coordinator | Product & Marketing | To Do | Medium | 2024-06-15 | 2024-08-15
Marketing & Branding Strategy
MAB-001 | Develop brand identity (logo, color palette, tone of voice) | Brand Strategist, Graphic Designer | Marketing & Creative | In Progress | High | 2024-04-15 | 2024-06-30
MAB-002 | Create content calendar and campaign strategy for pre-launch phase | Content Manager, Social Media Specialist | Marketing & Communications | To Do | Medium | 2024-05-30 | 2024-07-15
MAB-003 | Launch early adopter sign-up funnel and incentive program | Marketing Lead, Growth Hacker | Growth & Marketing | To Do | High | 2024-06-01 | 2024-08-31
Operations & Infrastructure Setup
OP-001 | Set up physical workspace or remote work infrastructure for team | Facilities Manager, IT Admin | Operations & IT | In Progress | Medium | 2024-04-15 | 2024-06-30
OP-002 | Finalize and implement core technology stack (cloud, dev tools, CI/CD) | CTO, DevOps Engineer | Engineering & IT | To Do | High | 2024-06-01 | 2024-08-15
HR & Recruitment Planning
HR-001 | Define team structure and create hiring plan for first 6 roles | HR Manager, CEO, Department Heads | Human Resources & Leadership | To Do | High | 2024-05-15 | 2024-07-15
HR-002 | Develop onboarding program and employee handbook templates | HR Lead, Legal Counsel | Human Resources & Legal | To Do | Medium | 2024-06-01 | 2024-07-31
Legend:Status – To Do, In Progress, Completed ¦ Priority – High (Red), Medium (Orange), Low (Green)