## Worksheet
Task | Owner | Due Date | Status | Priority | Notes
Define Vision Statement | Jane Doe | 2024-04-10 | Pending | High | Review with team leads.
Conduct Market Research | John Smith | 2024-04-15 | In Progress | High | Gather competitor data and customer insights.
Create MVP Prototype | Alice Brown | 2024-04-25 | Not Started | High | Include core features only.
Secure Initial Funding | Mike Wilson | 2024-05-01 | Pending | Urgent | Schedule pitch meetings with investors.
Hire Core Development Team | Sarah Lee | 2024-05-10 | Not Started | Medium | Candidates to be reviewed by HR.