## Worksheet
Task | Assigned To | Due Date | Status | Progress (%)
Define Startup Vision & Mission | CEO | 2023-10-15 | Pending | 0%
Develop Business Model Canvas | CPO, CTO | 2023-10-20 | In Progress | 65%
Market Research & Validation | Marketing Team | 2023-10-25 | In Progress | 45%
Create MVP Prototype | Product Team | 2023-11-05 | Pending | 0%
Fundraising Strategy Planning | COO, CFO | 2023-10-30 | In Progress | 75%
Hire Core Team Members | HR Manager | 2023-11-10 | Pending | 0%
Legal Structure & Registration | CFO, Legal Advisor | 2023-11-05 | Completed | 100%
Build Initial Website & Landing Page | Web Team | 2023-11-15 | In Progress | 50%
Develop Pitch Deck for Investors | CFO, CEO | 2023-11-20 | Pending | 0%
Set Up Development Environment & Tools | CTO, Dev Team | 2023-10-18 | Completed | 100%