## Startup Planning - Gantt Chart
Startup Planning - Gantt Chart (Basic)
Task | Start Date | End Date | Status | Progress (%)
Market Research | 2024-01-01 | 2024-01-15 | In Progress | 75
Business Plan Development | 2024-01-16 | 2024-02-15 | Pending | 30
Funding Proposal Drafting | 2024-01-16 | 2024-02-15 | Pending | 15
Team Hiring (Key Roles) | 2024-02-16 | 2024-03-31 | Pending | 5
Product Design & Prototyping | 2024-03-01 | 2024-05-31 | Pending | 10
Website Development | 2024-04-01 | 2024-06-30 | Pending | 8
Marketing Strategy & Branding | 2024-05-15 | 2024-06-30 | Pending | 12
Funding Round (Pitch) | 2024-06-15 | 2024-07-31 | Pending | 5
Launch Preparation & Testing | 2024-08-01 | 2024-09-30 | Pending | 3
Official Product Launch | 2024-10-01 | 2024-10-31 | Pending | 0