## Startup Planning - Gantt Chart
Startup Planning - Gantt Chart (Business Use)
Task | Start Date | End Date | Duration (Days) | Status | Progress
Phase 1: Idea & Market Research | 2024-03-01 | 2024-03-15 | 15 | In Progress
Define Target Market | 2024-03-01 | 2024-03-05 | 5 | In Progress
Competitor Analysis | 2024-03-06 | 2024-03-11 | 6 | In Progress
Validate Business Idea | 2024-03-12 | 2024-03-15 | 4 | In Progress
Phase 2: Product Development | 2024-03-16 | 2024-05-15 | 61 | Pending
Build MVP (Minimum Viable Product) | 2024-03-16 | 2024-04-15 | 31 | Pending
User Testing & Feedback Loop | 2024-04-16 | 2024-05-15 | 31 | Pending
Phase 3: Business & Financial Planning | 2024-05-16 | 2024-06-15 | 31 | Pending
Business Model Design | 2024-05-16 | 2024-05-31 | 16 | Pending
Financial Projections & Budgeting | 2024-06-01 | 2024-06-15 | 15 | Pending
Phase 4: Fundraising & Launch Preparation | 2024-06-16 | 2024-07-31 | 46 | Pending
Prepare Pitch Deck & Investor Materials | 2024-06-16 | 2024-06-30 | 15 | Pending
Initiate Fundraising Campaign | 2024-07-01 | 2024-07-31 | 31 | Pending
Milestone: MVP Complete | 2024-04-15 | 2024-04-15 | 1 | Not Reached
Milestone: Seed Funding Closed | 2024-07-31 | 2024-07-31 | 1 | Not Reached