## Worksheet
Startup Planning - Gantt Chart (Client View)
Project Timeline & Milestone Tracking for Strategic Development
Task ID | Task Description | Start Date | End Date | Status | Progress
T001 | Market Research & Validation | 2024-03-15 | 2024-04-30 | In Progress
Product Concept Design | Define Core Features & User Flows | 2024-04-15 | 2024-05-31 | In Progress
Prototype Development | Build MVP Version (v1.0) | 2024-05-15 | 2024-07-31 | Completed
User Testing & Feedback | Conduct Usability Studies (50 Users) | 2024-07-15 | 2024-08-31 | In Progress
Investor Pitch Preparation | Create Presentation & Financial Model | 2024-08-01 | 2024-09-30 | Delayed
Seed Funding Round | Secure $500K Investment | 2024-10-15 | 2024-11-30 | In Progress