## Worksheet
Task | Start Date | End Date | Duration (Days) | Owner | Status
Market Research | 2024-04-01 | 2024-04-15 | 15 | Alex Johnson | In Progress
Business Plan Draft | 2024-04-16 | 2024-05-01 | 16 | Sarah Kim | In Progress
Prototype Development | 2024-05-02 | 2024-06-15 | 45 | Mark Liu | In Progress
Fundraising Pitch Prep | 2024-06-16 | 2024-07-15 | 30 | Emily Zhang | Not Started
Launch Readiness Check | 2024-07-16 | 2024-07-31 | 16 | James Reed | Not Started
Product Launch | 2024-08-01 | 2024-08-01 | 1 | All Team | Scheduled