## Startup Planning - Gantt Chart
Startup Planning - Gantt Chart (Data Version)
Task ID | Task Name | Start Date | End Date | Duration (Days) | Status
1.01 | Market Research & Validation | 2024-04-01 | 2024-04-15 | 15 | In Progress
1.02 | Define Core Value Proposition | 2024-04-16 | 2024-04-25 | 10 | To Do
2.01 | Prototype Design (MVP) | 2024-04-26 | 2024-05-31 | 36 | To Do
2.02 | User Testing & Feedback Loop | 2024-06-01 | 2024-06-30 | 30 | To Do
3.01 | Develop Business Model Canvas | 2024-05-01 | 2024-05-15 | 15 | To Do
3.02 | Fundraising Plan & Pitch Deck | 2024-05-16 | 2024-06-15 | 31 | To Do
4.01 | Launch Strategy & Marketing Plan | 2024-06-16 | 2024-07-31 | 46 | To Do
M1 | Milestone: MVP Complete & Validated | 2024-05-31 | 2024-05-31 | 1 | Not Started
M2 | Milestone: Seed Funding Secured | 2024-07-15 | 2024-07-15 | 1 | Not Started
* This Gantt Chart template is for planning purposes and may be updated as the startup progresses.