## Worksheet
Task | Start Date | End Date | Duration (Days) | Status | Progress (%)
Market Research & Validation | 2024-01-05 | 2024-01-31 | 27 | In Progress | 65%
Define MVP Features | 2024-02-01 | 2024-02-15 | 15 | In Progress | 78%
Build Prototype (UI/UX) | 2024-02-16 | 2024-03-15 | 30 | Pending | 15%
Develop Core Backend System | 2024-03-01 | 2024-04-15 | 46 | Pending | 5%
User Testing & Feedback Loop | 2024-04-16 | 2024-05-15 | 30 | Pending | 0%
Iterate & Finalize MVP | 2024-05-16 | 2024-06-30 | 45 | Pending | 0%
Prepare Launch Plan & Marketing Strategy | 2024-06-01 | 2024-07-31 | 61 | Pending | 3%
Launch MVP (Soft Launch) | 2024-08-01 | 2024-08-31 | 31 | Pending | 0%
Monitor Metrics & Optimize Post-Launch | 2024-09-01 | 2024-12-31 | 122 | Pending | 0%
Total Duration: |  |  |  | 577 days