## Worksheet
Startup Planning - Employee View Gantt Chart
Employee Name | Role | Task / Milestone | Start Date | End Date | Status | Progress (%)
John Smith | Project Manager | Define Product Vision | 2024-01-05 | 2024-01-15 | In Progress | 65%
Jane Doe | UX Designer | Create Wireframes & Prototypes | 2024-01-10 | 2024-01-31 | In Progress | 75%
Mike Johnson | Frontend Developer | Build Landing Page | 2024-01-15 | 2024-02-10 | To Do | 5%
Sarah Wilson | Backend Developer | Design API Architecture | 2024-01-18 | 2024-02-05 | In Progress | 85%
Milestone: Product Prototype Complete (Target: Feb 12, 2024)
Tom Brown | Marketing Specialist | Develop Launch Strategy | 2024-01-20 | 2024-03-15 | To Do | 8%
Lisa Green | QA Engineer | Test Plan Development | 2024-01-25 | 2024-03-01 | To Do | 3%
David Lee | DevOps Engineer | Set Up CI/CD Pipeline | 2024-01-30 | 2024-03-15 | To Do | 5%
Milestone: First Version Ready for Beta Testing (Target: Mar 20, 2024)
Emily White | Customer Support Lead | Prepare Help Documentation | 2024-02-01 | 2024-03-31 | To Do | 1%
Chris Hall | Product Owner | Review Requirements & Feedback | 2024-02-15 | 2024-03-31 | To Do | 7%
Legend:
In Progress– Task is currently being worked on.
Milestone– Key deliverable or checkpoint in the timeline.
To Do– Task not yet started.
Note:This Gantt Chart is a visual representation of the employee-focused tasks in the Startup Planning phase. Actual dates and progress may vary.