## Worksheet
Startup Planning - Gantt Chart (Extended)
Task ID | Task Name | Start Date | End Date | Duration (Days) | Assigned To | Status
Phase 1: Idea & Research
1.1 | Market Research & Analysis | 2024-04-05 | 2024-05-15 | 41 | Jane Doe, Alex Lee | 68%
1.2 | Idea Validation (Surveys/Interviews) | 2024-05-16 | 2024-06-30 | 45 | Sarah Chen, Mark Taylor | 35%
M1 | Go/No-Go Decision Point | 2024-07-01 | 2024-07-05 | 5 | Peter Kim (CEO) | 100%
Phase 2: Product Development
2.1 | Product Concept & Wireframes | 2024-07-08 | 2024-08-15 | 39 | Lisa Wong, Tom Brown | 75%
2.2 | Figma Prototype Development | 2024-08-16 | 2024-09-30 | 46 | Ryan Patel, Emily Davis | 58%
M2 | Prototype Review & Approval | 2024-10-01 | 2024-10-15 | 15 | Lisa Wong (CTO) | 88%
Phase 3: Tech Build
3.1 | Frontend Development (React) | 2024-10-16 | 2025-01-31 | 77 | Dan Nguyen, Aisha Khan, Chris Lopez | 42%
3.2 | Backend Development (Node.js) | 2024-10-16 | 2025-01-31 | 77 | Maria Garcia, David Lee, Sophia Zhang | 54%
M3 | Alpha Release (Internal Testing) | 2025-02-01 | 2025-03-15 | 45 | All Dev Team & QA Lead | 7%
Phase 4: Testing & Refinement
4.1 | QA Test Plan Creation | 2025-03-16 | 2025-04-15 | 31 | Lisa Wong (CTO), QA Team Lead | 63%
4.2 | Internal & Beta Testing | 2025-04-16 | 2025-06-30 | 76 | Beta Testers, Dev Team, QA Team | 14%
M4 | Final Product Sign-Off | 2025-07-01 | 2025-07-15 | 15 | Peter Kim (CEO), CTO, CFO, Legal Team | 0%
Phase 5: Launch & Growth
5.1 | Marketing Campaign Planning | 2025-07-16 | 2025-08-31 | 47 | Maria Garcia (CMO), Marketing Team | 37%
5.2 | Website & App Launch | 2025-09-01 | 2025-11-30 | 91 | All Teams (Dev, Marketing, Support) | 8%
M5 | Official Product Launch | 2025-12-01 | 2025-12-03 | 3 | Peter Kim (CEO), All Executives, Marketing Team | 0%
Total Duration: |  |  |  | 638 days
Project Timeline: April 5, 2024 – December 3, 2025 ¦ Status as of May 18, 2024