## Worksheet
Startup Planning - Gantt Chart (Large Business)
Task ID | Task Name | Start Date | End Date | Duration (Days) | Status | Progress (%)
Phase 1 - Project Planning & Strategy
PLN-001 | Market Research & Analysis | 2024-04-01 | 2024-05-15 | 45 | In Progress | 67%
PLN-002 | Business Model Development | 2024-04-15 | 2024-06-30 | 76 | In Progress | 85%
PLN-003 | Business Plan Finalization | 2024-07-15 | 2024-07-15 | - | Completed | 100%
Phase 2 - Product Development
PRO-001 | Product Design & Prototyping | 2024-07-16 | 2024-11-30 | 137 | In Progress | 45%
PRO-002 | Software Development (MVP) | 2024-08-15 | 2025-03-31 | 261 | In Progress | 64%
PRO-003 | Quality Assurance & Testing | 2025-01-15 | 2025-04-30 | 106 | Delayed | 37%
Phase 3 - Launch Preparation
LAU-001 | Marketing & Branding Strategy | 2024-10-01 | 2025-06-30 | 273 | In Progress | 58%
LAU-002 | Customer Acquisition Plan | 2024-11-15 | 2025-08-31 | 263 | In Progress | 72%
LAU-003 | Launch Readiness Review | 2025-11-01 | 2025-11-07 | - | Delayed | 8%
Phase 4 - Post-Launch & Growth
POST-001 | Go-to-Market Launch (Q4 2025) | 2025-11-15 | 2026-03-31 | 178 | Delayed | 0%
POST-002 | Performance Analytics & Optimization | 2026-04-15 | 2027-12-31 | 649 | Delayed | 0%
Total Project Duration: | [5 empty] | 1027 days