## Worksheet
Startup Planning - Gantt Chart (Manager View)
Task ID | Task Name | Owner | Start Date | End Date | Status | Timeline (Month)
[5 empty] | Jan | Feb | Mar | Apr | May | Jun | Jul
1 | Market Research & Validation | Alice Chen | 2024-01-05 | 2024-03-15 | In Progress
2 | Product Design & Prototyping | James Reed | 2024-03-16 | 2024-05-31 | Pending Review
3 | MVP Development | Samir Patel | 2024-06-01 | 2024-11-30 | Scheduled
4 | Alpha Testing & Feedback | Lisa Kim | 2024-11-01 | 2025-01-31 | Not Started
5 | Product Launch & Go-to-Market | Derek Wong | 2025-02-15 | 2025-03-14 | Milestone
5.1 | Marketing Campaign Prep | Maria Gonzalez | 2024-09-01 | 2025-03-14 | In Progress
6 | Funding Round (Seed) | Robert Taylor | 2024-12-01 | 2025-03-31 | Pending Review
Total Project Duration | [6 empty] | Jan 2024 – Mar 2025
Overall Progress: