## Startup Planning - Gantt Chart
Startup Planning - Gantt Chart
Task | Start Date | End Date | Status | % Complete
Idea Validation & Market Research | 2024-01-01 | 2024-01-31 | In Progress | 75%
Business Model Development | 2024-02-01 | 2024-03-15 | In Progress | 65%
MVP Design & Prototyping | 2024-03-16 | 2024-05-31 | Not Started | 0%
User Testing & Feedback Collection | 2024-06-01 | 2024-07-31 | Not Started | 0%
Final Product Refinement | 2024-08-01 | 2024-08-31 | Not Started | 0%
MVP Launch (Go Live) | 2024-09-01 | 2024-09-15 | Milestone | 10%
Marketing & Customer Acquisition | 2024-09-16 | 2025-03-31 | Not Started | 0%
Funding Round Preparation & Pitching | 2025-01-01 | 2025-06-30 | Not Started | 0%
Funding Closed & Expansion Planning | 2025-07-01 | 2025-12-31 | Milestone | 5%
Total Timeline | 2024-01-01 | 2025-12-31 | Project Duration: 66 weeks ¦ Current Progress: 58%
Note: This Gantt chart is for planning purposes. Dates may be adjusted based on progress and feedback.