## Startup Planning Gantt Chart
Startup Planning Gantt Chart
Task | Start Date | End Date | Status | Progress
Market Research & Validation | 2024-01-01 | 2024-01-31 | In Progress
Product Development (MVP) | 2024-02-01 | 2024-05-31 | In Progress
Team Building & Infrastructure Setup | 2024-01-15 | 2024-03-31 | In Progress
Beta Testing & Feedback | 2024-06-01 | 2024-07-31 | Not Started
Marketing & Launch Prep | 2024-08-01 | 2024-08-31 | Not Started
Milestone: Product Launch | 2024-09-01 | 2024-09-15 | Milestone
Post-Launch Growth & Optimization | 2024-10-01 | 2025-12-31 | Not Started
Projected timeline for startup planning and execution using a professional Gantt chart format.