## Worksheet
Startup Planning - Gantt Chart Report
Task | Start Date | End Date | Status | Progress
Phase 1: Ideation & Market Research (Weeks 1-4)
Market Analysis | 2023-10-02 | 2023-10-15 | In Progress
Competitor Research | 2023-10-02 | 2023-10-15 | In Progress
Phase 2: Product Development (Weeks 5-12)
Product Design | 2023-10-16 | 2023-11-05 | In Progress
Prototype Development | 2023-11-06 | 2023-11-30 | To Do
Phase 3: Testing & Validation (Weeks 13-16)
User Testing | 2023-12-01 | 2023-12-15 | To Do
Feedback Integration | 2023-12-16 | 2023-12-30 | To Do
Phase 4: Launch Preparation (Weeks 17-20)
Marketing Campaign | 2024-01-01 | 2024-01-31 | To Do
Final Product Launch | 2024-02-15 | 2024-02-15 | Milestone
Generated on October 5, 2023 ¦ Startup Planning - Gantt Chart Report Version