## Startup Planning - Gantt Chart
Startup Planning - Gantt Chart (Simple)
Task | Start Date | End Date | Status | % Complete
Market Research & Validation | 2024-01-05 | 2024-01-31 | In Progress | 75%
Business Model Design | 2024-01-15 | 2024-02-14 | In Progress | 60%
Team Formation | 2024-01-31 | 2024-03-15 | Pending | 0%
Prototype Development | 2024-03-16 | 2024-05-31 | Pending | 0%
User Testing & Feedback | 2024-06-01 | 2024-07-31 | Pending | 0%
Funding Round Preparation | 2024-07-15 | 2024-08-31 | Pending | 0%
Product Launch (MVP) | 2024-09-01 | 2024-11-30 | Pending | 0%
Gantt Visualization
Market Research & ValidationBusiness Model DesignTeam FormationPrototype DevelopmentUser Testing & FeedbackFunding Round PreparationProduct Launch (MVP)
Legend:● In Progress,● On Track,● Upcoming Milestone